Miller-Driscoll PTA Job Description

Spring Carnival

Overview:  Plan and organize the PTA’s Spring Carnival. This is our largest fundraiser for the year.

Timeline

Miller-Driscoll Carnival - Tasks

- Planning & Logistics - Fall

- Secure Town Permit to hold event

- Be the main contact with Stewart Amusements (Richard Stewart)

- Signage - secure permits and place signs around town to promote event

- Arrange all needed items from school - custodians on duty, garbage cans available, tables for food, etc.

- Secure rentals of port-a-johns and dumpster

- Secure Police Dept coverage for all (or most) hours of carnival

- Sponsorship - January

- Create a packet of information to give to potential sponsors.  Packet should include the following:

  - The purpose of the PTA and how the school benefits from the funds raised (be specific and give examples).

  - A breakdown of the sponsorship levels. Be sure to include amount per level and benefits of each level

  - Sponsorship agreement form

- Approach various businesses in town - ask them to support our cause. Asking in person is more effective than in an email.

- Keep spreadsheet of sponsor’s levels and logo (if necessary).

- Coordinate those vendors who want to set up a table at the carnival for either Saturday or Sunday (weather dependent)

- Coordinate the printing of banners and t-shirts with sponsor logos.

- Pre-sale Wristbands & Volunteers  - Spring

- Create a flyer describing event and pre-sale wristband pricing and send home to all families 3-4 weeks before event

- Track pre-sale wristband purchases (by checks or paypal) and create spreadsheets of those families who paid in advance

- Distribute t-shirts the week of the carnival to those kids who purchased in advance, if applicable.

- Coordinate the sale of pre-sale wristbands at a local business the week of the event (used Tusk ‘n Cup last year)

- Create volunteer link to staff ticket booth all three days of event.  Manage the staffing of the booth all weekend - ensuring we have enough parent volunteers at all times.

- Media & Promotion - Spring

- Create Facebook page

- Write a press release describing event and send to various media outlets

- Contact News 12 and ask them to visit the event

Ongoing: As needed to provide event updates, attend PTA meetings and/or submit written report to be read into PTA minutes. Attendance at PTA meetings outside of providing event updates is always encouraged, however not required.

*All Committee Chairs must be members of the PTA per our By-Laws.

(Updated October 2017)